## Slide 1: Why WIP Matters
Understanding WIP in 5 Mins

## Slide 2: What is WIP?
WIP is…
  Work in progress
  The number of active stories a team is working on at any one time
  The number of balls a team is juggling at once.

## Slide 3: What we know about WIP?
As WIP increases…
  Team cognitive load increases
  Communication breaks down both between team members and from the team to others in the organization
  Team members silo and are less able to cover for each other
  Takes more time to deliver value (Little’s Law)
  Reduces agility of the team (ability to pivot)
  Defects increase
  Consistency of the team decreases
  etc.

## Slide 4: Fallacies of Utilization
Constantly busy (100% utilization) is not efficient
  Team members have a tendency to equate their busyness with how efficient they are as a team. These are completely different and many times not related.
  A team puts points on the board when they deliver value to the customer (user story completed).
  Every team member being busy actually slows down the teams delivery of value by added distractions, contention for scarce resources, increased risk / complexity, etc.
  It is not about how long you spent on the freeway but how you found the soonest, safest, happiest path to the destination (working software that creates early value).

## Slide 5: WIP Research
Accelerate
  Limiting WIP and Visualizing It (Chapter 7 – Management Practices for Software)
Larry Maccherone
  Little’s Law (direct relationship between WIP and cycle time)
  https://www.linkedin.com/in/larrymaccherone/detail/overlay-view/urn:li:fsd_profileTreasuryMedia:(ACoAAAAYbwwBnVliYKdPx3K3gRTawMSJb9MjjzI,50323466)/
Business Efficiency
  https://www.scrum.org/resources/blog/business-efficiency-watch-ball-not-player

## Slide 6: WIP Metric Guidance
The goal is to know the importance of WIP, track it, and keep it as low as feasible.
Rules of Thumb:
  WIP of 1 is fine
  WIP > (Dev Team Size / 2) would be cause for conversation as this means a team member is working solo
  ScrumMaster: WIP is the decision of the engineers HOWEVER be aware that this is a counter intuitive concept. You will need to coach, challenge, and educate on this.

## Slide 7: Questions?

## Slide 8: Why high WIP hurts communication
Member Ingestion
Production Defect
Exports
Report Ask
  Team members don’t listen well to their other team members because they care less.
  Team members spend more time confusing each other and trying to catch up on progress
  Teams members are less likely to ask for help when they should as they see it as disrupting their other team members

## Slide 9: Low WIP helps teams
Low WIP enables team members to…
  Pair program and cross-train more
  Spend time thinking about the overall effort of the story
  Cover for each other if someone steps away
  Expose bugs earlier in the development process due to active listening and participation of all team members on the same problem
  Pivot faster when priorities change as there are less things left in flight